## Gantt Chart
Pend | [7 empty] | Notes ➜ | [7 empty] | This is a living document, all dates (except for final due dates in RED) are subject to change. Dates blocked out in ORANGE will be adapted when the assignment becomes available.
PROJECT TITLE |  | Senior Design Feruta Pendulum | [5 empty] | COMPANY NAME | [8 empty] | PEND Senior Design Team
PROJECT MANAGERS |  | James Jones, Quinn Le, Drew Keller, Zachary Pinkley, Micheal Gareau | [5 empty] | DATE | [8 empty] | 2022-01-16
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | SPRING BREAK | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | FINALS WEEK
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
 | time axis 2022-01-09 to 2022-05-07
1 | Concept Design | Assigned To | Start | End | Duration | Completion
1.1 | Pendulum |  | 2022-01-16 | 2022-01-25 | 10 | 100% | bar: 2022-01-30
1.11 | Resizing Pendulum Links 1 & 2 | Zach | 2022-01-09 | 2022-01-16 | 8 | 100% | bar: 2022-01-09 to 2022-01-16; 2022-01-30
1.12 | Redesign how Links 1 & 2 Connect | Zach | 2022-01-09 | 2022-01-16 | 8 | 100% | bar: 2022-01-09 to 2022-01-16; 2022-01-30
1.13 | Redesign Structural Support for Links 1 & 2 | Zach | 2022-01-17 | 2022-01-20 | 4 | 100% | bar: 2022-01-17 to 2022-01-20; 2022-01-30
1.14 | Design integration of Pendulum to Encoder 1 | Zach | 2022-01-20 | 2022-01-23 | 4 | 100% | bar: 2022-01-20 to 2022-01-23; 2022-01-30
1.15 | Assemble Pendulum Subassembly in Solidworks | Zach | 2022-01-23 | 2022-01-25 | 3 | 100% | bar: 2022-01-23 to 2022-01-25; 2022-01-30
1.2 | Top |  | 2022-01-16 | 2022-01-25 | 10 | 100% | bar: 2022-01-30
1.21 | Design a Fixed platform to attach to the Frame | Quinn | 2022-01-17 | 2022-01-20 | 4 | 100% | bar: 2022-01-17 to 2022-01-20; 2022-01-30
1.22 | Design a rotating platform to sit ontop of the fixed platform | Zach | 2022-01-20 | 2022-01-23 | 4 | 100% | bar: 2022-01-20 to 2022-01-23; 2022-01-30
1.23 | Design connection between the rotating platform and the motor shaft | Quinn | 2022-01-23 | 2022-01-25 | 3 | 100% | bar: 2022-01-23 to 2022-01-25; 2022-01-30
1.24 | Reorganize Encoder 1 and Pendulum supports on rotating platform | Drew & Zach | 2022-01-20 | 2022-01-23 | 4 | 100% | bar: 2022-01-20 to 2022-01-23; 2022-01-30
1.25 | Provide clear routes for electrical wiring from Encoder to Slipring in Motor System | Drew | 2022-01-23 | 2022-01-25 | 3 | 100% | bar: 2022-01-23 to 2022-01-25; 2022-01-30
1.26 | Assemble Top Subassembly in Solidworks | Zach | 2022-01-23 | 2022-01-25 | 3 | 100% | bar: 2022-01-23 to 2022-01-25; 2022-01-30
1.3 | Motor |  | 2022-01-16 | 2022-01-25 | 10 | 100% | bar: 2022-01-30
1.31 | Redesign motor mount design to work with the new Frame design | Zach | 2022-01-17 | 2022-01-21 | 5 | 100% | bar: 2022-01-17 to 2022-01-21; 2022-01-30
1.32 | Solidify Slipring Choice & 3D Model It | James | 2022-01-17 | 2022-01-19 | 3 | 100% | bar: 2022-01-17 to 2022-01-19; 2022-01-30
1.33 | Secure Encoder 2 if needed | Michael | 2022-01-19 | 2022-01-22 | 4 | 100% | bar: 2022-01-19 to 2022-01-22; 2022-01-30
1.34 | Assemble Motor Subassembly in Solidworks | Zach | 2022-01-22 | 2022-01-23 | 2 | 100% | bar: 2022-01-22 to 2022-01-23; 2022-01-30
1.4 | Frame |  | 2022-01-16 | 2022-01-25 | 10 | 100% | bar: 2022-01-30
1.41 | Redesign frame to be rectangular with additional T-Slotted bars for Torque support | Zach | 2022-01-16 | 2022-01-20 | 5 | 100% | bar: 2022-01-16 to 2022-01-20; 2022-01-30
1.42 | Provide Fixture Locations for Electrical Components | Zach | 2022-01-21 | 2022-01-23 | 3 | 100% | bar: 2022-01-21 to 2022-01-23; 2022-01-30
1.43 | Assemble Frame Subassembly in Solidworks | Zach | 2022-01-23 | 2022-01-25 | 3 | 100% | bar: 2022-01-23 to 2022-01-25; 2022-01-30
1.5 | Panels |  | 2022-01-16 | 2022-01-25 | 10 | 100% | bar: 2022-01-30
1.51 | Redesign aesthetic outside panels to fit the frame's redesign | James | 2022-01-16 | 2022-01-20 | 5 | 100% | bar: 2022-01-16 to 2022-01-20; 2022-01-30
1.52 | Provide Routes for wiring from electrical components to a separate interface | James | 2022-01-21 | 2022-01-23 | 3 | 100% | bar: 2022-01-21 to 2022-01-23; 2022-01-30
1.53 | Assemble Panels Subassembly in Solidworks | James | 2022-01-23 | 2022-01-25 | 3 | 100% | bar: 2022-01-23 to 2022-01-25; 2022-01-30
1.6 | Get Approvel From Sponsor and Dr. Haight | PEND | 2022-01-19 | 2022-01-20 | 2 | 100% | bar: 2022-01-30
1.7 | Critical Design Report |  | 2022-01-26 | 2022-01-30 | 5 | 100% | bar: 2022-01-26 to 2022-01-30
1.71 | Update BOM | James | 2022-01-26 | 2022-01-30 | 5 | 100% | bar: 2022-01-26 to 2022-01-30
1.72 | Update Solidworks figures | Quinn | 2022-01-26 | 2022-01-30 | 5 | 100% | bar: 2022-01-26 to 2022-01-30
1.73 | Update Reference | Drew | 2022-01-26 | 2022-01-30 | 5 | 100% | bar: 2022-01-26 to 2022-01-30
1.74 | Update Design Description | Zach | 2022-01-26 | 2022-01-30 | 5 | 100% | bar: 2022-01-26 to 2022-01-30
1.75 | Update Schedule | Micheal | 2022-01-26 | 2022-01-30 | 5 | 100% | bar: 2022-01-26 to 2022-01-30
1.76 | Update Appendix | Micheal | 2022-01-28 | 2022-01-30 | 3 | 100% | bar: 2022-01-28 to 2022-01-30
1.77 | Update conclusions and recommendations | James | 2022-01-28 | 2022-01-30 | 3 | 100% | bar: 2022-01-28 to 2022-01-30
1.78 | Complete Social Impact TBD | Everyone | 2022-01-28 | 2022-01-30 | 3 | 0% | bar: 2022-01-30
1.79 | Complete Ethical Analysis TBD | Everyone | 2022-01-28 | 2022-01-30 | 3 | 0% | bar: 2022-01-30
1.71 | Update Table of content | Micheal | 2022-01-28 | 2022-01-30 | 3 | 100% | bar: 2022-01-28 to 2022-01-30
2 | Manufacturing | Assigned To | Start | End | Duration | Completion
2.1 | Raw Materials |  | 2022-01-28 | 2022-02-10 | 13 | 100% | bar: 2022-01-30
2.11 | Order and purchase parts | Michael/Nardos | 2022-01-30 | 2022-02-16 | 17 | 100% | bar: 2022-01-30 to 2022-02-16
2.12 | Recieve and Store purchased Parts | Pend | 2022-02-06 | 2022-02-20 | 15 | 100% | bar: 2022-01-30; 2022-02-06 to 2022-02-20
2.13 | Organize Purchased Parts | Pend | 2022-02-20 | 2022-02-20 | 1 | 100% | bar: 2022-01-30; 2022-02-20
2.2 | Machining |  | 2022-02-10 | 2022-02-24 | 15 | 95% | bar: 2022-01-30
2.21 | Mill out base and platforms | Michael/Zach | 2022-02-10 | 2022-02-14 | 5 | 100% | bar: 2022-01-30; 2022-02-10 to 2022-02-14
2.22 | Cut slotted T-frames to size | Michael/Zach | 2022-02-18 | 2022-02-20 | 3 | 100% | bar: 2022-01-30; 2022-02-18 to 2022-02-20
2.23 | Mill out holes on base and platforms for screws and wiring | Michael/Zach | 2022-02-10 | 2022-02-14 | 5 | 100% | bar: 2022-01-30; 2022-02-10 to 2022-02-14
2.24 | Mill out support brackets for T-frame assembly | Michael/Zach | 2022-02-20 | 2022-02-24 | 5 | 100% | bar: 2022-01-30; 2022-02-20 to 2022-02-24
2.25 | Cut Link rods to size, and resize them with Lathe | Michael/Zach | 2022-02-28 | 2022-03-02 | 3 | 100% | bar: 2022-01-30; 2022-02-28 to 2022-03-02
2.26 | Machine holes for the spinning disk and cut out the rubber track | Michael/Zach | 2022-03-02 | 2022-03-04 | 3 | 100% | bar: 2022-01-30; 2022-03-02 to 2022-03-04
2.27 | Machine a bearing plate for the stationary disk assembly | Micheal/Zach | 2022-03-09 | 2022-03-14 | 6 | 100% | bar: 2022-01-30; 2022-03-02 to 2022-03-04
2.3 | 3D Printing |  | 2022-01-30 | 2022-02-13 | 14 | 100% | bar: 2022-01-30; 2022-03-09 to 2022-03-14
2.31 | 3D Print the plastic pieces of the design | James | 2022-01-30 | 2022-02-06 | 7 | 100% | bar: 2022-01-30 to 2022-02-06
2.32 | Drill Holes into plastic as needed | James | 2022-02-04 | 2022-02-08 | 5 | 100% | bar: 2022-01-30; 2022-02-04 to 2022-02-08
2.33 | Finish 3D Print by Sanding and/or Polishing | James | 2022-02-08 | 2022-02-13 | 6 | 100% | bar: 2022-01-30; 2022-02-08 to 2022-02-13
2.4 | Tooling/Fixtures |  | 2/--/2022 | 2/--/2022 | #VALUE! | 0% | bar: 2022-01-30
2.41 | TBD |  |  |  |  | 100% | bar: 2022-01-30
2.5 | Assembly |  | 2022-02-25 | 2022-03-06 | 12 | 0% | bar: 2022-01-30
2.51 | Assemble T-Slotted Frame and Attach to the Base | Zach/James | 2022-02-28 | 2022-03-01 | 2 | 100% | bar: 2022-01-30; 2022-02-28 to 2022-03-01
2.511 | Secure support brackets to T-Slotted Frame | Zach/James | 2022-02-28 | 2022-03-01 | 2 | 100% | bar: 2022-01-30; 2022-02-28 to 2022-03-01
2.52 | Assemble Motor Subassembly in-place with the T-Slotted Frame | Quinn/Drew | 2022-03-01 | 2022-03-03 | 3 | 100% | bar: 2022-01-30; 2022-03-01 to 2022-03-03
2.521 | Secure shaft extension to motor, and slipring to extended shaft | Quinn/Drew | 2022-03-01 | 2022-03-03 | 3 | 100% | bar: 2022-01-30; 2022-03-01 to 2022-03-03
2.53 | Assemble Top Subassembly in-place ontop of the T-Slotted Frames | Zach | 2022-03-04 | 2022-03-06 | 3 | 100% | bar: 2022-01-30; 2022-03-04 to 2022-03-06
2.54 | Place and wire electrical components | TBD | 2022-03-03 | 2022-03-06 | 4 | 0% | bar: 2022-01-30; 2022-03-03 to 2022-03-06
2.55 | Assemble Pendulum Subassembly and insert it into Encoder 1 | Zach | 2022-03-04 | 2022-03-06 | 3 | 100% | bar: 2022-01-30; 2022-03-04 to 2022-03-06
3 | Testing | Assigned To | Start | End | Duration | Completion
3.1 | Force Tests |  | 2022-03-04 | 2022-03-11 | 8 | 0% | bar: 2022-01-30
3.12 | Ensure motor can withstand the axial force |  | 2022-03-07 | 2022-03-09 | 3 | 0% | bar: 2022-01-30; 2022-03-07 to 2022-03-09
3.13 | Ensure the encoder can withstand the bending moment |  | 2022-03-07 | 2022-03-09 | 3 | 0% | bar: 2022-01-30; 2022-03-07 to 2022-03-09
3.14 | Ensure the frame can withstand the torque applied to it |  | 2022-03-08 | 2022-03-10 | 3 | 100% | bar: 2022-01-30; 2022-03-08 to 2022-03-10
3.2 | Integration Tests |  | 2022-03-06 | 2022-03-06 | 1 | 0% | bar: 2022-01-30
3.22 | Ensure that each subassembly connects to other subassemblies correctly, and operates smoothly and without interference |  | 2022-03-06 | 2022-03-06 | 1 | 100% | bar: 2022-01-30; 2022-03-06
3.3 | Controls Test |  | 2022-03-11 | 2022-03-11 | 1 | 0% | bar: 2022-01-30
3.31 | Connect Prototype electrical components to Computer and the device to ensure no short circuits |  | 2022-03-11 | 2022-03-11 | 1 | 0% | bar: 2022-01-30; 2022-03-11
3.32 | Run Controllers to test if the Controller can balance the Pendulum reliably |  | 2022-03-11 | 2022-03-11 | 1 | 0% | bar: 2022-01-30; 2022-03-11
3.4 | Friction Test |  | 2022-03-11 | 2022-03-11 | 1 | 0% | bar: 2022-01-30
3.41 | Ensure that friction does not impede the movement of any rotating parts |  | 2022-03-11 | 2022-03-11 | 1 | 75% | bar: 2022-01-30; 2022-03-11
3.42 | Run Controls Test again and Monitor Friction of various parts |  | 2022-03-11 | 2022-03-11 | 1 | 0% | bar: 2022-01-30; 2022-03-11
4 | Final Deliverables | Assigned To | Start | End | Duration | Completion
4.1 | Prototype Demo and CATME Review |  | 2022-03-09 | 2022-03-18 | 10 | 100% | bar: 2022-01-30; 2022-03-18
4.11 | TBD when rubric is assigned |  |  |  |  | 100% | bar: 2022-01-30; 2022-03-18
4.2 | Final Poster and Project Video |  | 2022-04-10 | 2022-04-17 | 8 | 0% | bar: 2022-01-30; 2022-03-18
4.22 | Complete Poster draft to be reviewed in class |  | 2022-04-10 | 2022-04-14 |  | 100% | bar: 2022-01-30; 2022-03-18; 2022-04-10 to 2022-04-14
4.22 | Complete final poster |  | 2022-04-14 | 2022-04-17 |  | 100% | bar: 2022-01-30; 2022-03-18; 2022-04-14 to 2022-04-17
4.23 | Complete Project Video |  | 2022-04-14 | 2022-04-17 |  | 0% | bar: 2022-01-30; 2022-03-18; 2022-04-14 to 2022-04-17
4.3 | Senior Design Showcase |  | 2022-03-31 | 2022-04-28 | 29 | 0% | bar: 2022-01-30; 2022-03-18
4.31 | Complete Senior design showcase abstract |  | 2022-03-31 | 2022-04-03 |  | 100% | bar: 2022-01-30; 2022-03-18; 2022-03-31 to 2022-04-03
4.32 | Complete Senior design Brochure |  | 2022-03-31 | 2022-04-03 |  | 100% | bar: 2022-01-30; 2022-03-18; 2022-03-31 to 2022-04-03
| Showcase 4:00-5:00 |  | 2022-04-24 | 2022-04-28 |  | 0% | bar: 2022-01-30; 2022-03-18; 2022-04-24 to 2022-04-28
4.4 | FDR Presntation and Product Documentation |  | 2022-05-01 | 2022-05-05 | 5 | 0% | bar: 2022-01-30; 2022-03-18
4.41 | TBD when rubric is assigned |  |  |  |  | 0% | bar: 2022-01-30; 2022-03-18; 2022-05-01 to 2022-05-05
0% | bar: 2022-01-30; 2022-03-18
0% | bar: 2022-01-30; 2022-03-18; 2022-05-01 to 2022-05-05